## Slide 1
OCEAN’S FIVE

## Slide 2
Project:
OCEAN’S FIVE Movie Production
Meeting Purpose:
Quarterly Status Update
Presenters:
Simon Walker
??
??

## Slide 3
EXECUTIVE SUMMARY DASHBOARD
Produce and promote new movie: Ocean’s Five
Develop engaging screenplay
Secure cast & crew incl. the five ‘key talent’
Produce movie that resonates with target audience
Worldwide distribution - release in top 10 key markets by Christmas ’18
Worldwide box office receipts of $450M
PROJECT OBJECTIVES
STATUS SUMMARY & MILESTONES
Screenplay completed ahead of schedule, favorable focus group
Studio filming complete - ahead of schedule & under budget
Post-production on track – soundtrack complete (under budget)
Location filming - 6 weeks behind schedule,
  Relocation: Istanbul to Bangkok, over budget
Key Deliverables | Status / % Complete | Budget ($'000) | Spend vs Budget (YTD) |  | Projected final budget |  | Risk | Comments
 |  |  | ($'000) | % | ($'000) | % |  | 
Creative development - Screenplay & Script | 100% | $ 5,000 | $ (60) | 99% | $ 4,940 | 99% |  | Ahead of schedule, 87% strongly favorable response with target audience
Pre-Production - Assemble cast & crew | 100% | $ 50,000 | $ 2,200 | 104% | $ 52,200 | 104% |  | Higher fees for 2 key talent & Director
Production Overall | 85% | $ 45,000 | $ 5,800 | 113% | $ 48,800 | 108% |  | 10% vacancies in production crew
- Location filming | 75% | $ 30,000 | $ 6,500 | 122% | $ 34,500 | 115% |  | Relocation from Istanbul to Bangkok due to safety concerns and crew 6 weeks behind schedule
- Studio filming | 100% | $ 15,000 | $ (700) | 95% | $ 14,300 | 95% |  | Studio filming complete ahead of schedule
Post-production | 40% | $ 7,000 | $ (200) | 97% | $ 6,800 | 97% |  | Soundtrack recorded ahead of schedule
Marketing Campaign | 35% | $ 5,000 | $ - | 100% | $ 5,000 | 100% |  | Agency onboard, SOW agreed and planning complete
Total Budget |  | $ 112,000 | $ 13,540 | 112% | $ 117,740 | 105% |  | 
New locations identified & licenses secured
Bangkok filming commenced - recover some losses due to lower costs
Marketing campaign SOW agreed, campaign development kick-off mid Dec
WORK IN PROGRESS

## Slide 4
COMMUNICATION PLAN / STAKEHOLDER ANALYSIS
OCEAN’S FIVE

## Slide 5
COMMUNCATION SAMPLE
OCEAN’S FIVE
This could be the communication to the Executives informing them of the need to relocate from Istanbul to Bangkok due to security concerns and subsequent increase in costs

## Slide 6
ISSUE RESOLUTION
OCEAN’S FIVE
This needs to address the main issue of the project
Location filming - with increased security risks / concerns & escalating costs ($15M over original budget), needed to find an alternative location, adapt the script and reshoot some scenes, re-edit some footage in Istanbul so as to minimize wasted footage therefore minimizing losses and wasted time behind schedule

## Slide 7
DETAILED SCHEDULE
OCEAN’S FIVE
Gantt chart showing actual vs forecast